## Guidlines
WALBRO
Guidelines and Support
1 | This template has been developed to support Advanced Part Quality Planning (APQP) for Suppliers to Walbro Group. The template can be used for any project, part, or system.
2 | The requirements and PPAP submission level for submission will be determined by the Walbro Quality Representative.
3 | The Quality Representative will be responsible for providing the basic project information and placing an "X" in the "No Action Needed" column for activities which will NOT be followed-up by supplier under normal circumstances.
4 | The Supplier is responsible for identifying the responsible person in the "Responsibility" column and to establish the Due Date for each activity
5 | The Supplier is required to report progress by filling in the "Status" column and sending the entire APQP Tracker to the Walbro Quality representative on a regular basis. (Status explanation: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed)

## APQP
|  |  | ORIGINAL FORM CONTROLLED ONLY ON POLICYTECH UNCONTROLLED IF COPIED OR PRINTED | [9 empty] | Document #: F-8401-11
Document Owner: VP Quality
|  |  | Walbro Operating System | [9 empty] | Revision: 0 ¦ 06-Jun-18
APQP Tracker Form
| Walbro Part Number: |  |  |  |  | Supplier Name:
| Part Name: |  |  |  |  | Revision Level:
| APQP Launch Date: |  |  |  |  | APQP Tracker Revision Date:
| Supplier Team Members |  |  |  |  | Walbro Team Memebers
| Title |  |  | Name |  | Title |  |  |  | Name
| Project Manager |  |  |  |  | Project Manager
| Quality |  |  |  |  | Quality
| Engineering |  |  |  |  | Engineering
| Supply Chain/Purchasing |  |  |  |  | Supply Chain/Purchasing
Status explanation: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed. (see Symbols tab)
1 |  | Design Planning and Definition (For Suppliers with Design Resonsibility) |  |  | Responsibility | Due Date | Date Completed | Status | No Action Needed |  | Comments / Action Required | AIAG APQP reference
1.1 |  | Design goals and specification requirements set with input from Walbro
1.2 |  | Design Failure Mode and Effect Analysis (D-FMEA) complete | [9 empty] | 2.1
1.3 |  | Design For Manufacturability and Assembly (DFM/DFA) complete | [9 empty] | 2.2
1.4 |  | Cross-functional design reviews with Walbro | [9 empty] | 2.3; 2.4
1.5 |  | Engineering Drawings completed | [9 empty] | 2.6
1.6 |  | Engineering Specifications completed | [9 empty] | 2.7
1.7 |  | Material specifications set | [9 empty] | 2.8
1.8 |  | Drawing and Specification Changes has been documented | [9 empty] | 2.9
1.9 |  | Major and Critical Product and Process Characteristics determined | [9 empty] | 2.11
1.1 |  | Manufacturing of prototypes and prototype approval by Walbro
2 |  | Planning and Definition |  |  | Responsibility | Due Date | Date Completed | Status | No Action Needed |  | Comments / Action Required | AIAG APQP reference
2.1 |  | Supplier to review Drawing & specification | [9 empty] | 2.7
2.2 |  | Special/Critical Characteristics reviewed, Capability requirements confirmed | [9 empty] | 2.11
2.3 |  | Preliminary Process flow chart and Bill of material established | [9 empty] | 1.9; 1.10
2.4 |  | New Tooling, Equipment and Facilities requirements established | [9 empty] | 2.10
2.5 |  | New Gauges, Fixtures, and Testing equipment requirements established | [9 empty] | 2.12
2.6 |  | Initial capacity assessment done
2.7 |  | Sub-Suppliers identified with approved quality audits done
2.8 |  | Drawing & specification review with Walbro | [9 empty] | 2.7
2.9 |  | Feasibility study completed. | [9 empty] | 2.13
2.1 |  | Packaging plan reviewed with Walbro | [9 empty] | 3.1
3 |  | Manufacturing Process Design and Development |  |  | Responsibility | Due Date | Date Completed | Status | No Action Needed |  | Comments / Action Required | AIAG APQP reference
3.1 |  | Process Flow Charts created | [9 empty] | 3.3
3.2 |  | Process Failure Mode and Effect Analysis (P-FMEA) completed | [9 empty] | 3.6
3.3 |  | Preliminary Control Plan completed | [9 empty] | 3.7
3.4 |  | Measurement system analysis plan completed | [9 empty] | 3.9
3.5 |  | New Tooling, Equipment and Facilities obtained and installed | [9 empty] | 2.10; 2.12
3.6 |  | New Gauges, Fixtures, and Testing equipment obtained and installed | [9 empty] | 2.12
3.7 |  | Equipment set-up procedures established and documented
3.8 |  | Work instructions developed | [9 empty] | 3.8
3.9 |  | Training plan complete and implemented
3.1 |  | Sub-Supplier APQP plan completed
3.11 |  | Preliminary Walbro delivery plan received
3.12 |  | Preliminary Sub-Supplier delivery plan completed
4 |  | Engineering Samples |  |  | Responsibility | Due Date | Date Completed | Status | No Action Needed |  | Comments / Action Required | AIAG APQP reference
4.1 |  | Engineering samples requirements defined
4.2 |  | Sample delivery date
4.3 |  | Engineering samples available - design, dimensional, & material verification
5 |  | Significant Production Run Product and Process validation |  |  | Responsibility | Due Date | Date Completed | Status | No Action Needed |  | Comments / Action Required | AIAG APQP reference
5.1 |  | Production Control plan established | [9 empty] | 4.7
5.2 |  | Training of personnel completed
5.3 |  | Design FMEA (for suppliers that are design responsible) is complete | [9 empty] | 2.2.4
5.4 |  | Process Flow Diagram complete | [9 empty] | 2.2.5
5.5 |  | Process FMEA using AIAG format complete | [9 empty] | 2.2.6
5.6 |  | Control Plan is complete using AIAG format with all major and critical characteristics identified. | [9 empty] | 2.2.7
5.7 |  | Significant Production run complete | [9 empty] | 4.1
5.8 |  | Measurements System Analysis (MSA) | [9 empty] | 4.2
5.9 |  | Initial Process Potential Studies on all major and critical dimensions | [9 empty] | 2.2.11
5.1 |  | Process capability study(s) complete | [9 empty] | 4.3
5.11 |  | Scrap rate calculated and action plan established if needed.
5.12 |  | Capacity verified (Cycle/Tact Times verified)
5.13 |  | Packaging requirements verified to ensure part integrity at point of use | [9 empty] | 4.6
5.14 |  | Master sample stored at Supplier (Master sample of each multiple cavity die, tool or pattern - for future reference. | [9 empty] | AIAG PPAP Manual 2.2.15
6 |  | PPAP Documents for submission to Walbro Package must be submitted in the following order *Submit to Walbro 30 days before PPAP Submission |  |  | Responsibility | Due Date | Date Completed | Status | No Action Needed |  | Comments / Action Required | AIAG PPAP reference
6.1 |  | Walbro PPAP Package Review Form
6.2 |  | Part Submission Warrant (PSW) complete using the Walbro Warant | [9 empty] | 2.2.18; 4.1
6.3 |  | Inlcude Approved Engineering Change Documents that are not on the current production drawing | [9 empty] | 2.2.2
6.4 |  | Supplier Request for Deviation or Change forms, if any, have been submitted and approved by Walbro
6.5 |  | All Drawing dimenensions, notes, and materials are ballooned and assigned a number (numbers must be circled) | [9 empty] | 2.2.1
6.6 |  | Dimensional Results are complete using the Walbro Dimensional Report Form and all non-conformances clearly identified | [9 empty] | 2.2.9
6.7 |  | *Design FMEA (for suppliers that are design responsible) | [9 empty] | 2.2.4
6.8 |  | *Process Flow Chart | [9 empty] | 2.2.5
6.9 |  | *Process FMEA using AIAG format | [9 empty] | 2.2.6
6.1 |  | *Control Plan | [9 empty] | 2.2.7
6.11 |  | Measurement System Analysis Studies (MSA) | [9 empty] | 2.2.8
6.12 |  | Certification for all Checking Aids/Fixtures | [9 empty] | 2.2.16
6.13 |  | Initial Process Potential Studies | [9 empty] | 2.2.11
6.14 |  | Appearance Approval, Material Certificate of Analysis and Performance Test Results complete. (Blanket statements of conformance are not acceptable) | [9 empty] | 2.2.13; 2.2.12; 2.2.10
6.15 |  | *Records of Compliance with Walbro Specific Requirements Form complete. The Conflict Mineral Policy Statement and WEMDSL Information can be found on the Walbro.com supplier page | [9 empty] | 2.2.17
6.16 |  | Certificate of Compliance complete (for electronic components only) | [9 empty] | 2.2.17
6.17 |  | PPAP Sample Parts submited (must be from a significant production run) | [9 empty] | 2.2.14
6.18 |  | Other information as requested by Walbro | [9 empty] | 2.2.17
6.19 |  | PPAP Package Submitted to Walbro | [9 empty] | 2.2.17
7 |  | Walbro approval, Start of production & Delivery |  |  | Responsibility | Due Date | Date Completed | Status | No Action Needed |  | Comments / Action Required | AIAG APQP reference
7.1 |  | Walbro delivery plan received and confirmed
7.2 |  | Sub-Supplier delivery plan communicated and confirmed

## Symbols (cut & paste)
○
◔
◑
◕
●
No Action Needed